## Product Backlog
Day 4 – Assignment 3 Write Product Backlog and Sprint Backlog for Online Flight Booking System.
User Story ID | User Story | Description | Priority | Status | Remark
1 | Flight Search | Implement search functionality for flights between cities | High | in Progress | N/A
2 | Flight Booking | Implement booking process including personal details and payment | High | in Progress | N/A
3 | User Authentication | Implement user registration and login functionality | Medium | Completed | N/A
4 | Booking Management | Implement functionality to view and manage bookings | Medium | in Progress | N/A
5 | Flight Booking Cancellation | Implement cancellation functionality for booked flights | Medium | in Progress | N/A
6 | Payment Gateway Integration | Integrate payment gateway for processing payments | High | in Progress | N/A
7 | Notifications | Implement email notifications for booking confirmations and updates | Low | Completed | N/A
8 | Customer Support Chat | Implement a live chat feature for customer support | Low | Completed | N/A
9 | Mobile Responsiveness | Ensure the site is responsive and works well on mobile devices | Medium | Completed | N/A
10 | Performance Optimization | Optimize the system for better performance and faster load times | Low | in Progress | N/A

## Sprint Backlog 1
User Story ID | User Story | User Story Steps | Assigned Time | Estimated Time | Actual Time | Status
1 | Flight Search | As a user, I want to filter flight search results based on various criteria (price, airline, departure time, etc.) so that I can find flights that match my preferences quickly. | Jayashree | 5 hrs | 3 hrs
2 | Flight Booking | As a user, I want to view detailed information about a specific flight so that I can make an informed decision before booking. |  | 6 hrs | 5 hrs
3 | User Authentication | As a new user, I want to create an account on the flight booking platform so that I can manage my bookings and preferences |  | 3 hrs | 2 hrs
4 | Booking Management | As a user, I want to manage my flight bookings view and modify so that I can make changes to my travel plans as needed |  | 6 hrs | 6 hrs
5 | Flight Booking Cancellation | As a user, I want to manage my flight bookings cancel so that I can make changes to my travel plans as needed |  | 4 hrs | 3 hrs
6 | Payment Gateway Integration | As a user, I want to securely make payments for my flight bookings so that I can confirm my travel plans. |  | 7 hrs | 7 hrs

## Sprint Backlog 2
User Story ID | User Story | User Story Steps | Assigned Time | Estimated Time | Actual Time | Status
1 | Flight Search | As a developer, I need to fetch flight details from the database and display them on the UI so that users can view comprehensive information about each flight. | Jayashree | 5 hrs | 3 hrs
3 | User Authentication | As a developer, I need to create a registration form and backend logic so that users can register and activate their accounts. |  | 3 hrs | 2 hrs
4 | Booking Management | As a developer, I need to create a user dashboard where users can view and manage their bookings so that users have control over their travel plans. |  | 6 hrs | 6 hrs
5 | Flight Booking Cancellation | As a developer, I need to create a user dashboard where users can cancel their bookings so that users have control over their travel plans. |  | 4 hrs | 3 hrs
6 | Payment Gateway Integration | As a developer, I need to integrate a secure payment gateway (e.g., Stripe, PayPal) into the booking system so that users can make payments for their flight bookings. |  | 7 hrs | 7 hrs